## Air Assets
Item | Task/Piece | % Complete | Status | Est Complete Date | Graph
CH-53E | Model | 70% | In process
| Texture | 0% | Pending Model
| Animations | 0% | Pending Model
| Oxygen Work | 0% | Pending Model
| Testing / Troubleshooting | 0% | Pending All of the Above
| OVERALL | 14% | Pending Testing/Trouble Shooting
MH-60R | Model | 75% | In process
| Texture | 80% | Pending Model
| Animations | 0% | Pending Model
| Oxygen Work | 0% | Pending Model
| Testing / Troubleshooting | 0% | Pending All of the Above
| OVERALL | 31% | Pending Testing/Trouble Shooting
MH-60S | Model | 100% | In process
| Texture | 100% | Pending Model
| Animations | 100% | Pending Model
| Oxygen Work | 100% | Pending Model
| Testing / Troubleshooting | 0% | Pending All of the Above
| OVERALL | 80% | Pending Testing/Trouble Shooting
C-2 | Model | 99% | In process
| Texture | 0% | Pending Model
| Animations | 0% | Pending Model
| Oxygen Work | 0% | Pending Model
| Testing / Troubleshooting | 0% | Pending All of the Above
| OVERALL | 20% | Pending Testing/Trouble Shooting
T-45C | Model | 100% | In process
| Texture | 0% | Pending Model
| Animations | 0% | Pending Model
| Oxygen Work | 0% | Pending Model
| Testing / Troubleshooting | 0% | Pending All of the Above
| OVERALL | 20% | Pending Testing/Trouble Shooting